## Summary
SyndicSage V5 — Cost & Systems Overview
All amounts in EUR · Updated 2026-05-27
One-Time Setup | Monthly (MVP) | Annual (MVP) |  | Monthly at Scale | Break-Even (€49/mo plan)
Phase Cost Milestones
Phase | Name | New Services Added | Extra Monthly Cost | Cumulative Monthly
Phase 0-1 | Foundation + Shell | Supabase Pro, Railway, Vercel, GitHub Private | €61 | €61
Phase 2 | Core Data | Google Workspace (already set up) | €0 | €61
Phase 3 | Communication | Resend (free tier), Sentry (free tier) | €0 | €61
Phase 4 | Intelligence | Anthropic API (usage-based), Upstash Redis | €30 | €91
Phase 5 | Governance | No new services | €0 | €91
Phase 6 | Portal | Resend scaling (more emails) | €20 | €111
Phase 7 | Mobile | Apple Developer ($99/yr), Expo EAS Build | €18 | €129
Phase 8 | Launch | Vercel Pro (custom domain + bandwidth), DPA sign-offs | €20 | €149

## Monthly Costs
Monthly Recurring Costs
Total Monthly (MVP — Phase 0-3)
Total Monthly (Full — all phases)
Total Monthly at Scale (estimate)
Service | Category | Plan / Tier | EUR / Month | Phase | Status | Notes
Supabase | Infrastructure | Pro (EU region) | 25 | MVP | Required | PostgreSQL + Auth + Storage + Realtime. EU region mandatory for GDPR. Daily backups.
Railway — API | Infrastructure | Starter + usage | 8 | MVP | Required | Hono API server. ~€8/mo for small workloads. Scales with usage.
Railway — Worker | Infrastructure | Starter + usage | 7 | MVP | Required | BullMQ worker (email, scan, PDF, AI jobs). Separate service from API.
Vercel | Infrastructure | Hobby (free → Pro at launch) | 0 | MVP | Free now | Hobby supports custom domains. Upgrade to Pro (€20/mo) at launch for bandwidth + team.
GitHub | Development | Free → Team (private repo) | 0 | MVP | Free now | Switch to private before launch. Team plan: $4/user/mo. Solo: free with GitHub Pro ($4/mo).
Google Workspace | Communication | Business Starter | 6 | MVP | Active | hello@syndicsage.com already set up. MX records propagated 2026-05-24.
Upstash Redis | Infrastructure | Free tier → Pay-as-you-go | 0 | MVP | Free now | Rate limiting + BullMQ queue. Free: 10k commands/day. ~€5/mo at scale.
Resend | Communication | Free (3,000 emails/mo) | 0 | MVP | Free now | Transactional email. Free tier sufficient until Portal launch. Scale plan: €20/mo for 50k.
Sentry | Monitoring | Free (Developer) | 0 | MVP | Free now | Error tracking + performance. Free tier: 5k errors/mo. Team: $26/mo when needed.
Anthropic API | AI | Usage-based (Claude Sonnet) | 20 | Phase 4 | Required | AI Sage chat + extraction + summarization. €20/mo estimate for low usage. Scales with users.
Expo EAS Build | Mobile | Free → Production | 0 | Phase 7 | Free now | Mobile build service. Free: 30 builds/mo. Production plan: $99/mo if needed.
Vercel Pro | Infrastructure | Pro | 20 | Phase 8 | At launch | Upgrade at launch for bandwidth, analytics, team access. €20/mo.
GitHub Team | Development | Team (private) | 4 | Phase 8 | At launch | Switch to private repo before launch. $4/user/mo.
PostHog | Analytics | Free (1M events/mo) | 0 | Optional | Optional | Product analytics. Free tier covers early growth. No personal data needed.
Plausible | Analytics | Starter | 9 | Optional | Optional | Privacy-friendly analytics alternative to Google Analytics. GDPR-compliant.
TOTAL (all services)

## One-Time Costs
One-Time & Annual Costs
Total One-Time (Pre-Launch Minimum)
Total Annual (recurring yearly)
Item | Category | EUR | Priority | Frequency | Phase | Notes
Namecheap — syndicsage.com | Domain | 12 | Required | Annual | Live | Already purchased. Renews ~€12/yr. Includes DNS management.
Google Workspace | Communication | 72 | Required | Annual | Active | €6/mo = €72/yr. hello@syndicsage.com. MX records set.
EUIPO Trademark — SyndicSage | Legal | 900 | High | One-time | Pre-launch | Class 42+35. DIY via euipo.europa.eu Easy Filing. 4-6 months processing.
Privacy Policy + Terms of Use | Legal | 0 | Required | One-time | Pre-launch | Use iubenda.com (€27/yr) or lawyer (€500-2000). Must be live before first user.
GDPR DPA — Supabase | Legal/GDPR | 0 | Required | One-time | Pre-launch | Free. Sign via Supabase dashboard under Settings > Legal.
GDPR DPA — Vercel | Legal/GDPR | 0 | Required | One-time | Pre-launch | Free. Sign via Vercel dashboard under Settings > Legal.
GDPR DPA — Resend | Legal/GDPR | 0 | Required | One-time | Pre-launch | Free. Sign via Resend dashboard.
GDPR DPA — Anthropic | Legal/GDPR | 0 | Required | One-time | Phase 4 | Free. Anthropic provides standard DPA. Sign before AI features go live.
GDPR DPA — Railway | Legal/GDPR | 0 | Required | One-time | Pre-launch | Free. Contact Railway support for DPA.
Apple Developer Program | Mobile | 99 | Required | Annual | Phase 7 | Required to publish on App Store. $99/yr. Enables Apple Sign In on mobile.
Google Play Console | Mobile | 25 | Required | One-time | Phase 7 | One-time $25 registration fee to publish on Google Play.
iubenda Privacy Policy | Legal | 27 | Recommended | Annual | Pre-launch | GDPR-compliant privacy policy generator. Covers Belgium/EU. €27/yr.
Sentry Team Plan | Monitoring | 312 | Optional | Annual | Phase 3+ | $26/mo if free tier (5k errors/mo) is exceeded. Defer until needed.
Semgrep Pro | Security | 0 | Optional | Annual | Deferred | Free Community plan sufficient for solo founder. Pro when team grows.
External Pentest | Security | 2000 | Deferred | One-time | Phase 8+ | Trigger: first enterprise contract or €50k ARR. OWASP Top 10 + tenant isolation.
TOTAL ONE-TIME (Required only)

## Accounts & Access
All Accounts, Logins & Access — SyndicSage V5
Service | URL | Account / Login | Purpose | Tier | Status | Monthly Cost
Supabase | supabase.com | chrisndi-syn account | PostgreSQL DB + Auth + Storage + Realtime | Pro | Active | €25
Vercel | vercel.com | chrisndi-syn account | Frontend hosting — app.syndicsage.com | Hobby → Pro | Active | €0 → €20
Railway | railway.app | chrisndi-syn account | Hono API + BullMQ Worker hosting | Starter | Active | €15
GitHub | github.com/chrisndi-syn | chrisndi-syn | Source code — SyndicSage repo (go private!) | Free → Team | Public ⚠️ | €0 → €4
Google Workspace | workspace.google.com | hello@syndicsage.com | Business email + Google Sign In OAuth | Business Starter | Active | €6
Anthropic | console.anthropic.com | chris account | Claude API — AI Sage features | Pay-as-you-go | Ready | €20+
Namecheap | namecheap.com | chris account | syndicsage.com domain + DNS | Domain | Active | €1/mo
Resend | resend.com | chrisndi-syn account | Transactional email (invites, reminders) | Free | Set up | €0
Upstash | upstash.com | chrisndi-syn account | Redis — rate limiting + BullMQ queue | Free | Set up | €0
Sentry | sentry.io | chrisndi-syn account | Error tracking + performance monitoring | Free | Set up | €0
Apple Developer | developer.apple.com | chris Apple ID | App Store publishing + Apple Sign In | Standard ($99/yr) | Phase 7 | €8/mo
Google Play Console | play.google.com/console | chris Google account | Android app publishing | One-time €25 | Phase 7 | €0
EUIPO | euipo.europa.eu | chris account | SyndicSage trademark filing (Class 42+35) | €900 one-time | Pre-launch | €0
iubenda | iubenda.com | chris account | GDPR privacy policy + cookie policy | €27/yr | Pre-launch | €2/mo
PostHog | posthog.com | chrisndi-syn account | Product analytics (optional) | Free | Optional | €0

## Phase Rollout
Cost Rollout by Phase
Phase | Name | Services Activated | New Monthly Cost | Cumulative Monthly | One-Time This Phase | Cumulative One-Time | Notes
Phase 0 | Architecture Foundation | Supabase Pro, Railway API, Railway Worker, Upstash Redis (free) | 40 | 40 | 0 | 0 | Core infrastructure spun up. No users yet.
Phase 1 | Shell | GitHub Team (private repo), Google Workspace | 21 | 61 | 0 | 0 | Login page live. Repo goes private.
Phase 2 | Core Data | No new services | 0 | 61 | 0 | 0 | Buildings, owners, charges, settings.
Phase 2.5 | Audit Foundation | No new services | 0 | 61 | 0 | 0 | Audit log + GDPR table created.
Phase 3 | Communication | Resend (free), Sentry (free) | 0 | 61 | 0 | 0 | Documents, inbox, timeline, tickets.
Phase 4 | Intelligence | Anthropic API | 20 | 81 | 0 | 0 | AI Sage, extraction, RAG. Cost scales with usage.
Phase 5 | Governance | No new services | 0 | 81 | 0 | 0 | Roadmap, voting, meetings, reporting.
Phase 6 | Portal | Resend Scale (more emails) | 20 | 101 | 0 | 0 | Resident portal live. Email volume increases.
Phase 7 | Mobile | Apple Developer ($99/yr), Google Play (€25 once) | 8 | 109 | 124 | 124 | iOS + Android. Apple Dev €99/yr = €8/mo equiv.
Phase 8 | Launch | Vercel Pro, iubenda, trademark filed | 29 | 138 | 927 | 1051 | Vercel Pro €20 + iubenda €2 + GitHub Team already counted.

## Break-Even
Break-Even & Revenue Projection
Pricing Assumptions
Parameter | Value | Unit
Starter plan price | 49 | €/month per customer
Pro plan price | 99 | €/month per customer
Enterprise plan price | 199 | €/month per customer
Monthly costs (MVP) | 61 | €/month (Phase 0-3 baseline)
Monthly costs (Launch) | 138 | €/month (Phase 8 full)
Break-Even Analysis
Break-even (MVP costs, Starter plan)
Break-even (Launch costs, Starter plan)
Revenue Projection
Customers | Starter (€49) | Pro (€99) | Mixed (50/50) | Profit (Mixed - Launch costs)
1
2
3
5
10
20
50
100
Note: Break-even is at 3 customers on Starter plan (MVP phase). At launch costs, 3 customers still covers it. First €49 customer = profitable at MVP stage.

## Deferred Costs
Deferred & Future Costs (not in MVP budget)
Item | Estimated Cost | Frequency | Trigger | Notes
Self-hosted Supabase (EU VPS) | €20-50/mo | Monthly | Enterprise client requires on-premise | Supabase is open source — self-host entire stack on Hetzner/OVH EU VPS.
MinIO (document storage) | €10-30/mo | Monthly | On-premise contract or DPA requirement | S3-compatible. Same path structure. Zero code changes.
itsme® authentication | €0.10-0.30/tx | Per login | Enterprise/government customer request | OIDC — plugs into Supabase as custom OAuth. Contact itsme.be/business.
External pentest | €1,500-3,000 | One-time | First enterprise contract or €50k ARR | OWASP Top 10 + tenant isolation + file upload attack vectors.
LaunchDarkly (feature flags) | €0-350/mo | Monthly | Team grows beyond 3 devs | Current plan: feature_flags Supabase table (free). LaunchDarkly when ops complexity grows.
Read replica (Supabase) | ~€25/mo extra | Monthly | DB query latency > 200ms on list endpoints | Supabase one-click. Route reads to replica, writes to primary.
Kubernetes / EKS | €200+/mo | Monthly | Railway costs > €500/mo or GPU workloads needed | Hono is container-native — zero code changes to migrate.
SOC 2 / ISO 27001 audit | €5,000-20,000 | One-time | Enterprise procurement checklist | Architecture already designed to pass. AWS accounts needed for SOC 2.
Field-level encryption (KMS) | €50-100/mo | Monthly | Enterprise DPA requirement for IBAN/national IDs | packages/crypto + KMS-backed envelope encryption. Additive change.
Apple Developer (mobile) | €99/yr | Annual | Phase 7 — mobile app | Required for App Store. Already in One-Time budget.
Expo EAS Production build | $99/mo | Monthly | Mobile app CI/CD at scale | Free tier: 30 builds/mo. Upgrade when release cadence increases.
Multi-region (Vercel + Railway) | €50-100/mo | Monthly | Customers outside Belgium require low latency | Vercel edge already global. Railway: add EU + US regions.